## Sheet1
Sprint 1 | Roles | Team Members
| UI Developers | Praveen | Yuvaraj
| Backend Developers | Asha mol | Mano
| Devops/Tester | Karnisha
Efforts in Hours.
S.no | Task | Role | Timing
Creation of Project Folder Structure
Creation of Database Design
Table creation
Entity creation
Repository creation
Controller creation
Service creation
US1 | Create a Course
| UI Development (Validation and JEST) | UI | 8
| Backend Development (Controller, Services and NUnit) | Backend | 8
| API and Frontend Integration | Integration | 2
| Devops (CI/CD) | Deveops | 1
| Manual Testing and Automation Testing | Testing | 5
| R & D(Sharepoint) |  | 8
US2 | Create a Topics
| UI Development (Validation and JEST) | UI | 8
| Backend Development (Controller, Services and NUnit) | Backend | 8
| API and Frontend Integration | Integration | 2
| Devops (CI/CD) | Deveops | 1
| Manual Testing and Automation Testing | Testing | 5
| R & D |  | 8
US3 | Add a Video
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US4 | Add a Audio
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US5 | Add a Pdf
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US6 | Add a PPT
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US7 | Implementing Upload text in topic
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US8 | Implementing view video in admin page
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US9 | Implementing preview video in admin page
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US10 | Implementing view audio in admin page
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US11 | Implementing preview audio in admin page
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US12 | Implementing view video in user page (user)
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US13 | View the audio of the selected course (user)
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US14 | Modify Video content(replace the existing videos)
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US15 | Delete the existing video( remove the unwanted videos )
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US16 | Add additional video content( upload the additional videos )
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US17 | Modify audio content (replace the existing audio)
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US18 | Delete the existing audio( remove the unwanted audio )
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US19 | Update Audio (Upload Additional Audio):
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US20 | Update PDF(Replace Existing PDF):
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US21 | Delete PDF:
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US22 | Update PDF(Upload Additional PDF):
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US23 | Update PPT (Replace Existing PPT)
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US24 | Delete the existing ppt content
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US25 | Modify ppt content in the course (Upload additional content)
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US26 | Modify text content in the course (Replace the existing content)
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US27 | Delete the existing text content
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US28 | Modify text content in the course (Upload additional content)
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US29 | Manage the visibility status of course and content
| R&D For Progress Bar | UI
| UI Development (Validation and JEST) | Backend
| Backend Development (Controller, Services and NUnit) | Integration
| API and Frontend Integration | Deveops
| Devops (CI/CD) | Testing
Manual Testing and Automation Testing
R & D
US30 | Add a Category
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D
US31 | Edit and Delete the topic
| UI Development (Validation and JEST) | UI
| Backend Development (Controller, Services and NUnit) | Backend
| API and Frontend Integration | Integration
| Devops (CI/CD) | Deveops
| Manual Testing and Automation Testing | Testing
R & D